## Sheet1
| Project Name | Project Duration (in Days) | Project Start Date | Project End Date
| Restaurant Digital Marketing Solution | 60 | 2022-04-01 | 2022-05-31
| Task Id | Task
| 1 | Analysis and Elaboration
| 2 | Design
| 3 | Development
Task Id | Task Description | Planned Start Date | Task Duration | Planned End Date
1.1.1 | Identify Needs and Benefits
| Meet with Customers | 2022-04-01 | 2 | 2022-04-03
| Identify Needs and Project Constarints | 2022-04-02 | 1 | 2022-04-03
| Establish Prodcut Statement | 2022-04-04 | 1 | 2022-04-05
| Milestone: Product Statement Defined | 2022-04-05 | 0 | 2022-04-05
1.1.2 | Define Desired OCI
| Scope Keyboard Funtions | 2022-04-07 | 3 | 2022-04-10
| Scope Voice Input Functions | 2022-04-06 | 4 | 2022-04-10
| Scope Modes of Interaction | 2022-04-08 | 3 | 2022-04-11
| Scope Document Diagnosis | 2022-04-08 | 2 | 2022-04-10
| Scope Other WP Funstions | 2022-04-07 | 4 | 2022-04-11
| Document OCI | 2022-04-08 | 3 | 2022-04-11
| FTR: Review OCI with Customer | 2022-04-12 | 1 | 2022-04-13
| Revise OCI as Required | 2022-04-14 | 0 | 2022-04-14
| Milestone: OCI Defined | 2022-04-14 | 0 | 2022-04-14
1.1.3 | Define the Function
| Scope Keyboard Funtions | 2022-04-15 | 3 | 2022-04-18
| Scope Voice Input Functions | 2022-04-15 | 4 | 2022-04-19
| Describe Modes of Interaction | 2022-04-16 | 3 | 2022-04-19
| Describe Spell/Grammar Check | 2022-04-16 | 3 | 2022-04-19
| Describe Other WP Funstions | 2022-04-16 | 3 | 2022-04-19
| FTR: Review OCI Definition with Customer | 2022-04-20 | 1 | 2022-04-21
| Milestone: OCI Definition Complete | 2022-04-20 | 0 | 2022-04-20
1.1.4 | Isolation Software Elements
| Milestone: Software Elements Defined | 2022-04-20 | 1 | 2022-04-21
1.1.5 | Research
| Research Avalibility of Existing Software | 2022-04-20 | 1 | 2022-04-21
| Research Text Editing Components | 2022-04-22 | 1 | 2022-04-23
| Research Voice Input Components | 2022-04-23 | 1 | 2022-04-24
| Research File Management Components | 2022-04-20 | 1 | 2022-04-21
| Research Spell/Grammar Check Components | 2022-04-23 | 1 | 2022-04-24
| Milestone: Reusable Components Identified | 2022-04-24 | 0 | 2022-04-24
1.1.6 | Define Technical Feasiblity
| Evaluate Voice Input | 2022-04-25 | 4 | 2022-04-29
| Evaluate Grammar Checking | 2022-04-26 | 3 | 2022-04-29
| Milestone: Technical Feasiblity Assessed | 2022-04-29 | 0 | 2022-04-29
1.1.7 | Make Quick Estimate of Size | 2022-04-29 | 0 | 2022-04-29
1.1.8 | Create a Scope Definition
| Review Scope Document with Customer | 2022-04-30 | 0 | 2022-04-30
| Revise Document as Required | 2022-04-30 | 0 | 2022-04-30
| Milestone: Scope Document Complete | 2022-04-30 | 0 | 2022-04-30
2.1 | Design Database | 2022-04-30 | 3 | 2022-05-03
2.2 | Software Design | 2022-05-04 | 2 | 2022-05-06
2.3 | User Interface Design | 2022-05-07 | 1 | 2022-05-08
2.4 | Create Design Specification | 2022-05-09 | 4 | 2022-05-13
2.5 | Milestone: Design Complete | 2022-05-14 | 0 | 2022-05-14
3.1 | Deploy Development | 2022-05-15 | 1 | 2022-05-16
3.2 | Develop System Modules | 2022-05-17 | 8 | 2022-05-25
3.3 | Integrate System Modules | 2022-05-26 | 5 | 2022-05-31
[6 empty] | Start Date | Task Duration
[5 empty] | Meet with Customers | 2022-04-01 | 2
[5 empty] | Identify Needs and Project Constarints | 2022-04-02 | 1
[5 empty] | Establish Prodcut Statement | 2022-04-04 | 1
[5 empty] | Milestone: Product Statement Defined | 2022-04-05 | 0
[5 empty] | Scope Keyboard Funtions | 2022-04-07 | 3
[5 empty] | Scope Voice Input Functions | 2022-04-06 | 4
[5 empty] | Scope Modes of Interaction | 2022-04-08 | 3
[5 empty] | Scope Document Diagnosis | 2022-04-08 | 2
[5 empty] | Scope Other WP Funstions | 2022-04-07 | 4
[5 empty] | Document OCI | 2022-04-08 | 3
[5 empty] | FTR: Review OCI with Customer | 2022-04-12 | 1
[5 empty] | Revise OCI as Required | 2022-04-14 | 0
[5 empty] | Milestone: OCI Defined | 2022-04-14 | 0
[5 empty] | Scope Keyboard Funtions | 2022-04-15 | 3
[5 empty] | Scope Voice Input Functions | 2022-04-15 | 4
[5 empty] | Describe Modes of Interaction | 2022-04-16 | 3
[5 empty] | Describe Spell/Grammar Check | 2022-04-16 | 3
[5 empty] | Describe Other WP Funstions | 2022-04-16 | 3
[5 empty] | FTR: Review OCI Definition with Customer | 2022-04-20 | 1
[5 empty] | Milestone: OCI Definition Complete | 2022-04-20 | 0
[5 empty] | Milestone: Software Elements Defined | 2022-04-20 | 1
[5 empty] | Research Avalibility of Existing Software | 2022-04-20 | 1
[5 empty] | Research Text Editing Components | 2022-04-22 | 1
[5 empty] | Research Voice Input Components | 2022-04-23 | 1
[5 empty] | Research File Management Components | 2022-04-20 | 1
[5 empty] | Research Spell/Grammar Check Components | 2022-04-23 | 1
[5 empty] | Milestone: Reusable Components Identified | 2022-04-24 | 0
[5 empty] | Evaluate Voice Input | 2022-04-25 | 4
[5 empty] | Evaluate Grammar Checking | 2022-04-26 | 3
[5 empty] | Milestone: Technical Feasiblity Assessed | 2022-04-29 | 0
[5 empty] | Make Quick Estimate of Size | 2022-04-29 | 0
[5 empty] | Review Scope Document with Customer | 2022-04-30 | 0
[5 empty] | Revise Document as Required | 2022-04-30 | 0
[5 empty] | Milestone: Scope Document Complete | 2022-04-30 | 0
[5 empty] | Design Database | 2022-04-30 | 3
[5 empty] | Software Design | 2022-05-04 | 2
[5 empty] | User Interface Design | 2022-05-07 | 1
[5 empty] | Create Design Specification | 2022-05-09 | 4
[5 empty] | Milestone: Design Complete | 2022-05-14 | 0
[5 empty] | Deploy Development | 2022-05-15 | 1
[5 empty] | Develop System Modules | 2022-05-17 | 8
[5 empty] | Integrate System Modules | 2022-05-26 | 5
Formulas:
Project End Date = [Project Duration (in Days)]+[Project Start Date]